## Read me
Delivery Health Model
Three WiredTiger storage engine teams, two-week sprints, April 2025 to October 2026. Source: MongoDB public Jira, project WT.
Sheets
Summary: say-do ratio, scope added and carry-over by team, all live formulas over the Sprints sheet.
Sprints: one row per sprint. Blue cells are data, black cells are formulas.
Flow: one row per finished item, with cycle time split by status.
Capacity planner: the formula from the Sprint Planning Field Guide. Change the blue inputs.
Definitions
Committed: in the sprint two hours after it started, rebuilt from each ticket history.
Say-do ratio: committed items done by sprint end, divided by committed items.
Scope added: items that joined the sprint after it started, divided by committed items.
Built by Jeffrey Okonkwo.

## Summary
Delivery health by team
Team | Sprints | Committed | Committed done | Say-do ratio | Added | Scope added % | Carried over | Sprints at 80%+
SE Foundations | 30 | 175 | 99 | 56.57% | 103 | 58.86% | 97 | 9
SE Persistence | 28 | 61 | 21 | 34.43% | 146 | 239.3% | 64 | 3
SE Transactions | 37 | 536 | 230 | 42.91% | 271 | 50.56% | 281 | 4
Program | 95 | 772 | 350 | 45.34% | 520 | 67.36% | 442 | 16
Say-do ratio by half year
Team | Apr to Dec 2025 | Jan to Oct 2026 | Change
SE Foundations | 50% | 60% | 10%
SE Persistence | 37.78% | 25% | -12.78%
SE Transactions | 58.59% | 39.36% | -19.23%

## Sprints
Team | Sprint | Start | End | Half | Committed | Committed done | Added | Added done | Carried over | Removed | Say-do ratio | Scope added % | Carry-over % | Hit 80%?
SE Foundations | SE Foundations - 2025-05-09 | 2025-04-28 | 2025-05-09 | Apr to Dec 2025 | 5 | 0 | 3 | 3 | 5 | 0 | 0% | 60% | 62.5% | No
SE Foundations | SE Foundations - 2025-05-23 | 2025-05-13 | 2025-05-23 | Apr to Dec 2025 | 4 | 1 | 1 | 0 | 4 | 0 | 25% | 25% | 80% | No
SE Foundations | SE Foundations - 2025-06-06 | 2025-05-23 | 2025-06-06 | Apr to Dec 2025 | 8 | 4 | 2 | 1 | 4 | 1 | 50% | 25% | 40% | No
SE Foundations | SE Foundations - 2025-06-20 | 2025-06-06 | 2025-06-20 | Apr to Dec 2025 | 6 | 6 | 3 | 2 | 1 | 0 | 100% | 50% | 11.11% | Yes
SE Foundations | SE Foundations - 2025-07-04 | 2025-06-20 | 2025-07-04 | Apr to Dec 2025 | 2 | 1 | 1 | 1 | 1 | 0 | 50% | 50% | 33.33% | No
SE Foundations | SE Foundations - 2025-07-18 | 2025-07-04 | 2025-07-18 | Apr to Dec 2025 | 0 | 0 | 0 | 0 | 0 | 0
SE Foundations | SE Foundations - 2025-08-01 | 2025-07-18 | 2025-08-01 | Apr to Dec 2025 | 3 | 0 | 0 | 0 | 3 | 0 | 0% | 0% | 100% | No
SE Foundations | SE Foundations - 2025-08-15 | 2025-08-01 | 2025-08-15 | Apr to Dec 2025 | 5 | 1 | 2 | 2 | 3 | 1 | 20% | 40% | 42.86% | No
SE Foundations | SE Foundations - 2025-08-29 | 2025-08-15 | 2025-08-29 | Apr to Dec 2025 | 5 | 4 | 2 | 0 | 3 | 0 | 80% | 40% | 42.86% | Yes
SE Foundations | SE Foundations - 2025-09-12 | 2025-08-29 | 2025-09-12 | Apr to Dec 2025 | 6 | 5 | 3 | 2 | 1 | 1 | 83.33% | 50% | 11.11% | Yes
SE Foundations | SE Foundations - 2025-09-26 | 2025-09-12 | 2025-09-26 | Apr to Dec 2025 | 4 | 1 | 4 | 1 | 4 | 0 | 25% | 100% | 50% | No
SE Foundations | SE Foundations - 2025-10-10 | 2025-09-26 | 2025-10-09 | Apr to Dec 2025 | 1 | 0 | 3 | 3 | 1 | 0 | 0% | 300% | 25% | No
SE Foundations | SE Foundations - 2025-10-24 | 2025-10-12 | 2025-10-23 | Apr to Dec 2025 | 5 | 4 | 6 | 5 | 0 | 1 | 80% | 120% | 0% | Yes
SE Foundations | SE Foundations - 2025-11-07 | 2025-10-24 | 2025-11-06 | Apr to Dec 2025 | 1 | 1 | 1 | 1 | 0 | 0 | 100% | 100% | 0% | Yes
SE Foundations | SE Foundations - 2025-11-21 | 2025-11-06 | 2025-11-20 | Apr to Dec 2025 | 5 | 2 | 3 | 2 | 3 | 1 | 40% | 60% | 37.5% | No
SE Foundations | SE Foundations - 2026-01-02 | 2025-12-19 | 2026-01-04 | Apr to Dec 2025 | 0 | 0 | 1 | 0 | 1 | 0 |  |  | 100%
SE Foundations | SE Foundations - 2026-01-16 | 2026-01-05 | 2026-01-15 | Jan to Oct 2026 | 1 | 1 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | Yes
SE Foundations | SE Foundations - 2026-02-27 | 2026-01-29 | 2026-02-27 | Jan to Oct 2026 | 1 | 1 | 2 | 0 | 2 | 0 | 100% | 200% | 66.67% | Yes
SE Foundations | SE Foundations - 2026-04-10 | 2026-03-30 | 2026-04-09 | Jan to Oct 2026 | 1 | 0 | 0 | 0 | 1 | 0 | 0% | 0% | 100% | No
SE Foundations | SE Foundations - 2026-04-24 | 2026-04-10 | 2026-04-23 | Jan to Oct 2026 | 2 | 0 | 1 | 0 | 3 | 0 | 0% | 50% | 100% | No
SE Foundations | SE Foundations - 2026-05-08 | 2026-04-23 | 2026-05-14 | Jan to Oct 2026 | 9 | 3 | 4 | 4 | 5 | 1 | 33.33% | 44.44% | 38.46% | No
SE Foundations | SE Foundations - 2026-06-09 | 2026-05-22 | 2026-06-08 | Jan to Oct 2026 | 12 | 11 | 3 | 2 | 1 | 0 | 91.67% | 25% | 6.667% | Yes
SE Foundations | SE Foundations - 2026-06-23 | 2026-06-09 | 2026-06-22 | Jan to Oct 2026 | 13 | 8 | 2 | 1 | 6 | 0 | 61.54% | 15.38% | 40% | No
SE Foundations | SE Foundations - 2026-07-07 | 2026-06-22 | 2026-07-06 | Jan to Oct 2026 | 10 | 5 | 8 | 3 | 8 | 1 | 50% | 80% | 44.44% | No
SE Foundations | SE Foundations - 2026-07-21 | 2026-07-07 | 2026-07-22 | Jan to Oct 2026 | 12 | 9 | 8 | 2 | 7 | 0 | 75% | 66.67% | 35% | No
SE Foundations | SE Foundations - 2026-08-04 | 2026-07-22 | 2026-08-04 | Jan to Oct 2026 | 12 | 7 | 12 | 7 | 7 | 1 | 58.33% | 100% | 29.17% | No
SE Foundations | SE Foundations - 2026-08-18 | 2026-08-04 | 2026-08-17 | Jan to Oct 2026 | 9 | 6 | 8 | 6 | 4 | 1 | 66.67% | 88.89% | 23.53% | No
SE Foundations | SE Foundations - 2026-09-01 | 2026-08-18 | 2026-09-02 | Jan to Oct 2026 | 6 | 5 | 9 | 7 | 2 | 1 | 83.33% | 150% | 13.33% | Yes
SE Foundations | SE Foundations - 2026-09-29 | 2026-09-17 | 2026-09-28 | Jan to Oct 2026 | 13 | 6 | 7 | 5 | 8 | 1 | 46.15% | 53.85% | 40% | No
SE Foundations | SE Foundations - 2026-10-13 | 2026-09-29 | 2026-10-12 | Jan to Oct 2026 | 14 | 7 | 4 | 2 | 9 | 0 | 50% | 28.57% | 50% | No
SE Persistence | SE Persistence - 2025-05-09 | 2025-04-30 | 2025-05-13 | Apr to Dec 2025 | 3 | 3 | 6 | 3 | 3 | 0 | 100% | 200% | 33.33% | Yes
SE Persistence | SE Persistence - 2025-05-23 | 2025-05-13 | 2025-05-28 | Apr to Dec 2025 | 3 | 1 | 6 | 0 | 6 | 1 | 33.33% | 200% | 66.67% | No
SE Persistence | SE Persistence - 2025-06-06 | 2025-05-28 | 2025-06-06 | Apr to Dec 2025 | 6 | 1 | 1 | 0 | 5 | 1 | 16.67% | 16.67% | 71.43% | No
SE Persistence | SE Persistence - 2025-06-20 | 2025-06-06 | 2025-06-20 | Apr to Dec 2025 | 5 | 2 | 7 | 3 | 6 | 1 | 40% | 140% | 50% | No
SE Persistence | SE Persistence - 2025-07-04 | 2025-06-22 | 2025-07-06 | Apr to Dec 2025 | 8 | 2 | 2 | 0 | 3 | 5 | 25% | 25% | 30% | No
SE Persistence | SE Persistence - 04/07-21/07 | 2025-07-06 | 2025-07-22 | Apr to Dec 2025 | 3 | 0 | 2 | 1 | 3 | 1 | 0% | 66.67% | 60% | No
SE Persistence | SE Persistence - 2025-08-01 | 2025-07-22 | 2025-07-31 | Apr to Dec 2025 | 3 | 1 | 0 | 0 | 2 | 0 | 33.33% | 0% | 66.67% | No
SE Persistence | SE Persistence - 2025-08-15 | 2025-07-31 | 2025-08-14 | Apr to Dec 2025 | 2 | 0 | 2 | 2 | 2 | 0 | 0% | 100% | 50% | No
SE Persistence | SE Persistence - 2025-08-29 | 2025-08-14 | 2025-08-28 | Apr to Dec 2025 | 2 | 1 | 1 | 1 | 1 | 0 | 50% | 50% | 33.33% | No
SE Persistence | SE Persistence - 2025-09-12 | 2025-09-01 | 2025-09-11 | Apr to Dec 2025 | 0 | 0 | 3 | 2 | 0 | 0 |  |  | 0%
SE Persistence | SE Persistence - 2025-09-26 | 2025-09-11 | 2025-09-25 | Apr to Dec 2025 | 0 | 0 | 3 | 3 | 0 | 0 |  |  | 0%
SE Persistence | SE Persistence - 2025-10-10 | 2025-09-25 | 2025-10-09 | Apr to Dec 2025 | 0 | 0 | 1 | 0 | 1 | 0 |  |  | 100%
SE Persistence | SE Persistence - 2025-10-24 | 2025-10-13 | 2025-10-23 | Apr to Dec 2025 | 2 | 1 | 9 | 8 | 1 | 1 | 50% | 450% | 9.091% | No
SE Persistence | SE Persistence - 2025-11-07 | 2025-10-24 | 2025-11-07 | Apr to Dec 2025 | 0 | 0 | 14 | 9 | 4 | 0 |  |  | 28.57%
SE Persistence | SE Persistence - 2025-11-21 | 2025-11-07 | 2025-11-21 | Apr to Dec 2025 | 4 | 1 | 15 | 13 | 4 | 1 | 25% | 375% | 21.05% | No
SE Persistence | SE Persistence - 2025-12-05 | 2025-11-21 | 2025-12-05 | Apr to Dec 2025 | 4 | 4 | 13 | 12 | 1 | 0 | 100% | 325% | 5.882% | Yes
SE Persistence | SE Persistence - 2025-12-19 | 2025-12-07 | 2025-12-19 | Apr to Dec 2025 | 0 | 0 | 2 | 2 | 0 | 0 |  |  | 0%
SE Persistence | SE Persistence - 2026-01-02 | 2025-12-19 | 2026-01-02 | Apr to Dec 2025 | 0 | 0 | 2 | 1 | 1 | 0 |  |  | 50%
SE Persistence | SE Persistence - 2026-01-16 | 2026-01-01 | 2026-01-15 | Jan to Oct 2026 | 0 | 0 | 9 | 9 | 0 | 0 |  |  | 0%
SE Persistence | SE Persistence - 2026-01-30 | 2026-01-15 | 2026-01-29 | Jan to Oct 2026 | 0 | 0 | 3 | 2 | 1 | 0 |  |  | 33.33%
SE Persistence | SE Persistence - 2026-02-13 | 2026-01-29 | 2026-02-12 | Jan to Oct 2026 | 1 | 0 | 4 | 3 | 2 | 0 | 0% | 400% | 40% | No
SE Persistence | SE Persistence - 2026-02-27 | 2026-02-13 | 2026-02-27 | Jan to Oct 2026 | 2 | 1 | 8 | 8 | 0 | 1 | 50% | 400% | 0% | No
SE Persistence | SE Persistence - 2026-03-13 | 2026-02-27 | 2026-03-13 | Jan to Oct 2026 | 1 | 1 | 4 | 4 | 0 | 0 | 100% | 400% | 0% | Yes
SE Persistence | SE Persistence - 2026-03-27 | 2026-03-13 | 2026-03-27 | Jan to Oct 2026 | 0 | 0 | 21 | 10 | 8 | 0 |  |  | 38.1%
SE Persistence | SE Persistence - 2026-05-08 | 2026-04-24 | 2026-05-08 | Jan to Oct 2026 | 4 | 2 | 6 | 5 | 3 | 0 | 50% | 150% | 30% | No
SE Persistence | SE Persistence - 2026-05-22 | 2026-05-08 | 2026-05-22 | Jan to Oct 2026 | 3 | 0 | 2 | 2 | 3 | 0 | 0% | 66.67% | 60% | No
SE Persistence | SE Persistence - 2026-06-05 | 2026-05-22 | 2026-06-05 | Jan to Oct 2026 | 3 | 0 | 0 | 0 | 2 | 1 | 0% | 0% | 66.67% | No
SE Persistence | SE Persistence - 2026-06-19 | 2026-06-05 | 2026-06-19 | Jan to Oct 2026 | 2 | 0 | 0 | 0 | 2 | 0 | 0% | 0% | 100% | No
SE Transactions | SE Transactions - 2025-05-09 | 2025-04-27 | 2025-05-09 | Apr to Dec 2025 | 7 | 3 | 4 | 4 | 4 | 0 | 42.86% | 57.14% | 36.36% | No
SE Transactions | SE Transactions - 2025-06-06 | 2025-05-23 | 2025-06-06 | Apr to Dec 2025 | 3 | 3 | 11 | 10 | 1 | 0 | 100% | 366.7% | 7.143% | Yes
SE Transactions | SE Transactions - 2025-06-20 | 2025-06-06 | 2025-06-20 | Apr to Dec 2025 | 6 | 5 | 3 | 0 | 4 | 0 | 83.33% | 50% | 44.44% | Yes
SE Transactions | SE Transactions - 2025-07-04 | 2025-06-20 | 2025-07-04 | Apr to Dec 2025 | 10 | 6 | 2 | 2 | 0 | 4 | 60% | 20% | 0% | No
SE Transactions | SE Transactions - 2025-07-18 | 2025-07-09 | 2025-07-18 | Apr to Dec 2025 | 2 | 1 | 0 | 0 | 1 | 0 | 50% | 0% | 50% | No
SE Transactions | SE Transactions - 2025-08-01 | 2025-07-18 | 2025-08-01 | Apr to Dec 2025 | 7 | 4 | 1 | 1 | 2 | 1 | 57.14% | 14.29% | 25% | No
SE Transactions | SE Transactions - 2025-08-15 | 2025-08-01 | 2025-08-15 | Apr to Dec 2025 | 4 | 2 | 1 | 1 | 2 | 0 | 50% | 25% | 40% | No
SE Transactions | SE Transactions - 2025-08-29 | 2025-08-15 | 2025-08-29 | Apr to Dec 2025 | 10 | 7 | 4 | 4 | 3 | 0 | 70% | 40% | 21.43% | No
SE Transactions | SE Transactions - 2025-09-12 | 2025-08-29 | 2025-09-12 | Apr to Dec 2025 | 7 | 5 | 5 | 4 | 2 | 1 | 71.43% | 71.43% | 16.67% | No
SE Transactions | SE Transactions - 2025-09-26 | 2025-09-12 | 2025-09-26 | Apr to Dec 2025 | 6 | 4 | 6 | 4 | 3 | 1 | 66.67% | 100% | 25% | No
SE Transactions | SE Transactions - 2025-10-10 | 2025-09-26 | 2025-10-10 | Apr to Dec 2025 | 5 | 1 | 1 | 0 | 3 | 2 | 20% | 20% | 50% | No
SE Transactions | SE Transactions - 2025-10-24 | 2025-10-10 | 2025-10-24 | Apr to Dec 2025 | 8 | 3 | 3 | 3 | 2 | 3 | 37.5% | 37.5% | 18.18% | No
SE Transactions | SE Transactions - 2025-11-07 | 2025-10-24 | 2025-11-07 | Apr to Dec 2025 | 3 | 2 | 3 | 3 | 0 | 1 | 66.67% | 100% | 0% | No
SE Transactions | SE Transactions - 2025-11-21 | 2025-11-07 | 2025-11-21 | Apr to Dec 2025 | 6 | 6 | 2 | 2 | 0 | 0 | 100% | 33.33% | 0% | Yes
SE Transactions | SE Transactions - 2025-12-05 | 2025-11-21 | 2025-12-05 | Apr to Dec 2025 | 4 | 3 | 4 | 4 | 1 | 0 | 75% | 100% | 12.5% | No
SE Transactions | SE Transactions - 2025-12-19 | 2025-12-05 | 2025-12-19 | Apr to Dec 2025 | 4 | 2 | 4 | 3 | 1 | 1 | 50% | 100% | 12.5% | No
SE Transactions | SE Transactions - 2026-01-02 | 2025-12-19 | 2026-01-02 | Apr to Dec 2025 | 7 | 1 | 0 | 0 | 4 | 2 | 14.29% | 0% | 57.14% | No
SE Transactions | SE Transactions - 2026-01-16 | 2026-01-02 | 2026-01-16 | Jan to Oct 2026 | 9 | 2 | 10 | 9 | 7 | 1 | 22.22% | 111.1% | 36.84% | No
SE Transactions | SE Transactions - 2026-01-30 | 2026-01-16 | 2026-01-30 | Jan to Oct 2026 | 15 | 1 | 2 | 2 | 3 | 11 | 6.667% | 13.33% | 17.65% | No
SE Transactions | SE Transactions - 2026-02-13 | 2026-02-03 | 2026-02-13 | Jan to Oct 2026 | 7 | 2 | 4 | 2 | 3 | 4 | 28.57% | 57.14% | 27.27% | No
SE Transactions | SE Transactions - 2026-02-27 | 2026-02-13 | 2026-02-27 | Jan to Oct 2026 | 9 | 2 | 5 | 3 | 6 | 3 | 22.22% | 55.56% | 42.86% | No
SE Transactions | SE Transactions - 2026-03-13 | 2026-02-27 | 2026-03-13 | Jan to Oct 2026 | 7 | 4 | 3 | 2 | 3 | 1 | 57.14% | 42.86% | 30% | No
SE Transactions | SE Transactions - 2026-03-27 | 2026-03-13 | 2026-03-27 | Jan to Oct 2026 | 8 | 1 | 1 | 0 | 2 | 6 | 12.5% | 12.5% | 22.22% | No
SE Transactions | SE Transactions - 2026-04-10 | 2026-03-27 | 2026-04-10 | Jan to Oct 2026 | 12 | 1 | 4 | 0 | 15 | 0 | 8.333% | 33.33% | 93.75% | No
SE Transactions | SE Transactions - 2026-04-24 | 2026-04-10 | 2026-04-24 | Jan to Oct 2026 | 16 | 11 | 4 | 3 | 3 | 3 | 68.75% | 25% | 15% | No
SE Transactions | SE Transactions - 2026-05-08 | 2026-04-24 | 2026-05-08 | Jan to Oct 2026 | 16 | 5 | 9 | 5 | 14 | 1 | 31.25% | 56.25% | 56% | No
SE Transactions | SE Transactions - 2026-05-22 | 2026-05-08 | 2026-05-22 | Jan to Oct 2026 | 15 | 3 | 19 | 14 | 14 | 3 | 20% | 126.7% | 41.18% | No
SE Transactions | SE Transactions - 2026-06-05 | 2026-05-22 | 2026-06-05 | Jan to Oct 2026 | 20 | 16 | 26 | 20 | 10 | 0 | 80% | 130% | 21.74% | Yes
SE Transactions | SE Transactions - 2026-06-19 | 2026-06-05 | 2026-06-19 | Jan to Oct 2026 | 32 | 12 | 7 | 6 | 21 | 0 | 37.5% | 21.88% | 53.85% | No
SE Transactions | SE Transactions - 2026-07-03 | 2026-06-22 | 2026-07-03 | Jan to Oct 2026 | 43 | 10 | 9 | 7 | 22 | 13 | 23.26% | 20.93% | 42.31% | No
SE Transactions | SE Transactions - 2026-07-17 | 2026-07-03 | 2026-07-17 | Jan to Oct 2026 | 29 | 13 | 15 | 10 | 16 | 5 | 44.83% | 51.72% | 36.36% | No
SE Transactions | SE Transactions - 2026-07-31 | 2026-07-17 | 2026-07-31 | Jan to Oct 2026 | 25 | 14 | 10 | 6 | 11 | 4 | 56% | 40% | 31.43% | No
SE Transactions | SE Transactions - 2026-08-14 | 2026-07-31 | 2026-08-14 | Jan to Oct 2026 | 27 | 18 | 22 | 18 | 10 | 2 | 66.67% | 81.48% | 20.41% | No
SE Transactions | SE Transactions - 2026-08-28 | 2026-08-14 | 2026-08-28 | Jan to Oct 2026 | 24 | 15 | 26 | 18 | 17 | 0 | 62.5% | 108.3% | 34% | No
SE Transactions | SE Transactions - 2026-09-11 | 2026-08-28 | 2026-09-11 | Jan to Oct 2026 | 43 | 28 | 24 | 18 | 21 | 0 | 65.12% | 55.81% | 31.34% | No
SE Transactions | SE Transactions - 2026-09-25 | 2026-09-11 | 2026-09-25 | Jan to Oct 2026 | 43 | 12 | 8 | 4 | 34 | 0 | 27.91% | 18.6% | 66.67% | No
SE Transactions | SE Transactions - 2026-10-09 | 2026-09-25 | 2026-10-09 | Jan to Oct 2026 | 37 | 2 | 9 | 4 | 16 | 23 | 5.405% | 24.32% | 34.78% | No

## Flow
Item | Team | Type | Started | Done | Cycle days | Working days | Code review days | Blocked days | Other waiting days | Flow efficiency
WT-10779 | SE Persistence | Task | 2026-02-10 | 2026-06-29 | 139.11 | 33.82 | 0 | 11.06 | 94.24 | 24.31%
WT-10792 | SE Persistence | Bug | 2025-03-13 | 2025-05-05 | 53.11 | 16.81 | 27.17 | 0 | 9.13 | 31.65%
WT-11177 | SE Persistence | New Feature | 2025-07-24 | 2025-09-01 | 38.82 | 5 | 33.82 | 0 | 0 | 12.88%
WT-12542 | SE Foundations | Bug | 2025-06-02 | 2025-06-18 | 15.93 | 10.86 | 5.08 | 0 | 0 | 68.17%
WT-13368 | SE Persistence | Bug | 2025-04-30 | 2025-05-07 | 6.99 | 1.88 | 5.1 | 0 | 0 | 26.9%
WT-13430 | SE Foundations | Bug | 2024-08-30 | 2025-11-13 | 439.99 | 74.83 | 0.78 | 0 | 364.38 | 17.01%
WT-13454 | SE Foundations | Improvement | 2025-09-19 | 2025-10-17 | 27.84 | 12.89 | 14.95 | 0 | 0 | 46.3%
WT-13551 | SE Persistence | Build Failure | 2025-05-22 | 2025-07-04 | 42.92 | 25.65 | 0 | 0 | 17.28 | 59.76%
WT-13627 | SE Transactions | Bug | 2025-05-30 | 2025-06-04 | 4.9 | 4.9 | 0 | 0 | 0 | 100%
WT-13703 | SE Transactions | Bug | 2025-03-03 | 2025-05-26 | 84.11 | 21.78 | 4.26 | 0 | 58.07 | 25.89%
WT-13747 | SE Persistence | Task | 2025-04-07 | 2025-05-01 | 24.07 | 3.12 | 20.95 | 0 | 0 | 12.96%
WT-14091 | SE Foundations | Improvement | 2025-05-26 | 2025-05-28 | 2.12 | 1.19 | 0.93 | 0 | 0 | 56.13%
WT-14123 | SE Foundations | Improvement | 2025-03-06 | 2025-06-16 | 102.07 | 12.33 | 3.92 | 4.57 | 81.24 | 12.08%
WT-14127 | SE Foundations | Task | 2025-04-03 | 2025-05-05 | 32.14 | 8.33 | 4.22 | 12.25 | 7.35 | 25.92%
WT-14140 | SE Transactions | Bug | 2025-03-12 | 2025-05-26 | 74.27 | 8.52 | 23.81 | 0 | 29.76 | 11.47%
WT-14204 | SE Persistence | Task | 2025-05-05 | 2025-06-11 | 37.23 | 32.04 | 5.18 | 0 | 0 | 86.06%
WT-14267 | SE Transactions | Build Failure | 2025-04-28 | 2025-05-13 | 14.98 | 6.44 | 6.25 | 0 | 1.43 | 42.99%
WT-14270 | SE Foundations | Build Failure | 2025-04-08 | 2025-06-04 | 57.1 | 15.62 | 0.99 | 0 | 40.49 | 27.36%
WT-14312 | SE Persistence | Improvement | 2025-06-18 | 2025-06-19 | 1.03 | 0 | 1.03 | 0 | 0 | 0%
WT-14323 | SE Foundations | Build Failure | 2025-04-16 | 2025-05-18 | 32.77 | 19.65 | 2.89 | 0 | 10.23 | 59.96%
WT-14336 | SE Transactions | Task | 2025-05-21 | 2025-05-23 | 1.6 | 0.02 | 1.57 | 0 | 0 | 1.25%
WT-14343 | SE Transactions | Task | 2025-05-12 | 2025-05-14 | 2.13 | 2.13 | 0 | 0 | 0 | 100%
WT-14345 | SE Transactions | Task | 2025-05-02 | 2025-05-05 | 3.9 | 3.9 | 0 | 0 | 0 | 100%
WT-14355 | SE Persistence | Bug | 2025-05-01 | 2025-05-05 | 3.93 | 0 | 3.93 | 0 | 0 | 0%
WT-14365 | SE Transactions | Task | 2025-08-07 | 2025-08-22 | 14.15 | 4.31 | 9.83 | 0 | 0 | 30.46%
WT-14391 | SE Persistence | Bug | 2025-04-14 | 2025-04-30 | 15.37 | 0 | 15.37 | 0 | 0 | 0%
WT-14393 | SE Transactions | Task | 2025-04-15 | 2025-04-29 | 13.96 | 0.43 | 13.52 | 0 | 0 | 3.08%
WT-14449 | SE Foundations | Bug | 2025-06-16 | 2025-06-16 | 0.07 | 0.07 | 0 | 0 | 0 | 100%
WT-14455 | SE Transactions | Bug | 2025-04-29 | 2025-04-30 | 0.46 | 0.01 | 0.45 | 0 | 0 | 2.174%
WT-14461 | SE Foundations | Bug | 2025-05-29 | 2025-06-19 | 20.26 | 0.16 | 7.03 | 13.06 | 0 | 0.7897%
WT-14551 | SE Foundations | Bug | 2025-05-06 | 2025-05-09 | 2.05 | 0.05 | 2 | 0 | 0 | 2.439%
WT-14557 | SE Transactions | Task | 2025-05-03 | 2025-05-06 | 2.94 | 2.94 | 0 | 0 | 0 | 100%
WT-14568 | SE Foundations | Build Failure | 2025-05-07 | 2025-05-08 | 0.93 | 0.63 | 0.3 | 0 | 0 | 67.74%
WT-14570 | SE Persistence | Task | 2025-05-20 | 2025-06-17 | 28.01 | 0.02 | 7.6 | 0 | 2.52 | 0.0714%
WT-14590 | SE Transactions | New Feature | 2025-06-30 | 2025-07-14 | 14.67 | 0 | 0 | 0 | 14.67 | 0%
WT-14606 | SE Transactions | Task | 2025-05-30 | 2025-06-04 | 5.76 | 0 | 5.76 | 0 | 0 | 0%
WT-14616 | SE Transactions | Task | 2025-05-27 | 2025-06-03 | 6.2 | 6.2 | 0 | 0 | 0 | 100%
WT-14622 | SE Transactions | Build Failure | 2026-08-21 | 2026-08-21 | 0.1 | 0 | 0.1 | 0 | 0 | 0%
WT-14631 | SE Transactions | Bug | 2025-05-26 | 2025-05-26 | 0.41 | 0 | 0.41 | 0 | 0 | 0%
WT-14633 | SE Transactions | Task | 2025-05-27 | 2025-05-30 | 3.11 | 1.91 | 1.2 | 0 | 0 | 61.41%
WT-14636 | SE Foundations | Task | 2025-08-19 | 2025-09-10 | 22.02 | 12.58 | 0 | 1.78 | 7.67 | 57.13%
WT-14640 | SE Persistence | Improvement | 2026-03-31 | 2026-10-07 | 189.92 | 6.49 | 1.07 | 0 | 182.35 | 3.417%
WT-14643 | SE Foundations | Improvement | 2025-05-30 | 2025-06-17 | 18.14 | 7.24 | 10.9 | 0 | 0 | 39.91%
WT-14647 | SE Persistence | Documentation | 2025-05-30 | 2026-07-16 | 412.14 | 31.68 | 0 | 359.35 | 21.11 | 7.687%
WT-14652 | SE Foundations | Story | 2025-06-27 | 2025-07-01 | 4.06 | 4.06 | 0 | 0 | 0 | 100%
WT-14654 | SE Transactions | Bug | 2025-06-03 | 2025-06-20 | 16.22 | 12.41 | 0 | 0 | 3.81 | 76.51%
WT-14657 | SE Transactions | Task | 2025-06-03 | 2025-06-04 | 1.21 | 1.21 | 0 | 0 | 0 | 100%
WT-14690 | SE Persistence | Task | 2025-07-15 | 2025-07-17 | 2.8 | 2.8 | 0 | 0 | 0 | 100%
WT-14699 | SE Persistence | Task | 2025-06-23 | 2025-06-30 | 7.17 | 3.09 | 4.07 | 0 | 0 | 43.1%
WT-14715 | SE Transactions | Task | 2025-07-22 | 2025-07-28 | 6.18 | 6.18 | 0 | 0 | 0 | 100%
WT-14724 | SE Transactions | Task | 2025-06-13 | 2025-06-16 | 3.43 | 0.36 | 3.07 | 0 | 0 | 10.5%
WT-14726 | SE Transactions | Task | 2025-06-18 | 2025-06-18 | 0 | 0 | 0 | 0 | 0
WT-14729 | SE Transactions | Task | 2025-06-19 | 2025-06-20 | 1.05 | 1.05 | 0 | 0 | 0 | 100%
WT-14730 | SE Foundations | Task | 2026-07-30 | 2026-08-11 | 12.02 | 4.08 | 7.93 | 0 | 0 | 33.94%
WT-14759 | SE Persistence | Task | 2025-06-12 | 2025-06-12 | 0 | 0 | 0 | 0 | 0
WT-14760 | SE Foundations | Build Failure | 2025-08-12 | 2025-08-25 | 13.07 | 6.54 | 0 | 0 | 6.52 | 50.04%
WT-14762 | SE Foundations | Bug | 2025-06-11 | 2025-06-11 | 0.3 | 0 | 0.3 | 0 | 0 | 0%
WT-14776 | SE Persistence | Build Failure | 2025-06-16 | 2025-06-18 | 1.15 | 1.15 | 0 | 0 | 0 | 100%
WT-14802 | SE Transactions | Task | 2025-06-23 | 2025-06-25 | 2.04 | 0.91 | 1.13 | 0 | 0 | 44.61%
WT-14804 | SE Transactions | Build Failure | 2025-06-18 | 2025-06-23 | 5 | 1.49 | 3.51 | 0 | 0 | 29.8%
WT-14809 | SE Transactions | Improvement | 2025-06-18 | 2025-06-25 | 7.08 | 7.08 | 0 | 0 | 0 | 100%
WT-14816 | SE Persistence | Task | 2025-06-24 | 2025-06-25 | 0.74 | 0 | 0 | 0 | 0.74 | 0%
WT-14841 | SE Transactions | Task | 2025-06-23 | 2025-06-23 | 0.15 | 0.02 | 0.13 | 0 | 0 | 13.33%
WT-14843 | SE Transactions | Improvement | 2025-06-26 | 2025-07-14 | 17.74 | 0 | 0 | 0 | 0 | 0%
WT-14852 | SE Transactions | Bug | 2025-07-08 | 2025-07-17 | 9.18 | 9.18 | 0 | 0 | 0 | 100%
WT-14879 | SE Transactions | New Feature | 2025-10-12 | 2026-05-29 | 228.34 | 2.26 | 0 | 0 | 226.08 | 0.9898%
WT-14941 | SE Transactions | Task | 2025-07-28 | 2025-08-07 | 9.95 | 7.19 | 2.76 | 0 | 0 | 72.26%
WT-14988 | SE Persistence | Task | 2025-07-11 | 2025-08-25 | 45.08 | 21.16 | 4.02 | 0 | 19.9 | 46.94%
WT-14989 | SE Transactions | Task | 2025-08-25 | 2025-08-26 | 1.09 | 0 | 1.08 | 0 | 0 | 0%
WT-15011 | SE Transactions | Improvement | 2025-08-28 | 2025-09-01 | 4.12 | 0.19 | 3.93 | 0 | 0 | 4.612%
WT-15031 | SE Foundations | Task | 2025-08-04 | 2025-08-28 | 24.26 | 22.66 | 0 | 0 | 1.6 | 93.4%
WT-15065 | SE Transactions | Improvement | 2025-07-27 | 2025-07-30 | 2.7 | 2.7 | 0 | 0 | 0 | 100%
WT-15099 | SE Transactions | Bug | 2025-08-21 | 2025-08-21 | 0.02 | 0.02 | 0 | 0 | 0 | 100%
WT-15108 | SE Foundations | Documentation | 2025-08-01 | 2025-08-13 | 12.68 | 5.96 | 6.72 | 0 | 0 | 47%
WT-15140 | SE Transactions | Task | 2025-10-20 | 2025-10-23 | 2.55 | 1.19 | 1.36 | 0 | 0 | 46.67%
WT-15147 | SE Transactions | Build Failure | 2025-08-18 | 2025-08-19 | 0.06 | 0.01 | 0.04 | 0 | 0 | 16.67%
WT-15165 | SE Transactions | Task | 2025-08-19 | 2025-09-01 | 13.16 | 13.15 | 0.01 | 0 | 0 | 99.92%
WT-15168 | SE Foundations | Improvement | 2025-08-18 | 2025-08-26 | 7.91 | 0.99 | 6.92 | 0 | 0 | 12.52%
WT-15209 | SE Transactions | New Feature | 2025-08-19 | 2025-08-25 | 6.29 | 6.29 | 0 | 0 | 0 | 100%
WT-15270 | SE Transactions | Bug | 2025-09-09 | 2025-09-09 | 0.55 | 0.55 | 0 | 0 | 0 | 100%
WT-15296 | SE Transactions | Build Failure | 2025-09-30 | 2025-10-07 | 7.18 | 7.18 | 0 | 0 | 0 | 100%
WT-15302 | SE Foundations | Bug | 2025-09-02 | 2025-09-05 | 3.01 | 0.02 | 3 | 0 | 0 | 0.6645%
WT-15316 | SE Foundations | Task | 2025-08-29 | 2025-09-01 | 2.12 | 0 | 2.12 | 0 | 0 | 0%
WT-15346 | SE Transactions | Task | 2025-09-04 | 2025-09-23 | 19.13 | 19.13 | 0 | 0 | 0 | 100%
WT-15350 | SE Transactions | Task | 2025-09-02 | 2025-09-08 | 5.84 | 5.84 | 0 | 0 | 0 | 100%
WT-15375 | SE Foundations | Task | 2025-09-04 | 2025-09-22 | 17.19 | 0.02 | 17.17 | 0 | 0 | 0.1163%
WT-15380 | SE Transactions | Task | 2026-04-01 | 2026-04-13 | 12.3 | 0.11 | 12.19 | 0 | 0 | 0.8943%
WT-15390 | SE Foundations | Build Failure | 2025-11-16 | 2025-11-18 | 1.03 | 0.94 | 0.08 | 0 | 0 | 91.26%
WT-15465 | SE Transactions | Task | 2025-12-29 | 2026-01-05 | 6.97 | 0.8 | 6.17 | 0 | 0 | 11.48%
WT-15477 | SE Transactions | New Feature | 2025-10-07 | 2025-10-13 | 5.79 | 0 | 5.79 | 0 | 0 | 0%
WT-15484 | SE Foundations | Task | 2025-09-16 | 2025-09-17 | 0.78 | 0 | 0.78 | 0 | 0 | 0%
WT-15485 | SE Transactions | New Feature | 2025-09-16 | 2025-09-22 | 5.88 | 0.01 | 5.87 | 0 | 0 | 0.1701%
WT-15538 | SE Transactions | Task | 2025-10-07 | 2026-02-16 | 132.83 | 6.65 | 0 | 0 | 122.54 | 5.006%
WT-15558 | SE Transactions | Improvement | 2025-09-23 | 2026-04-21 | 210.14 | 0.01 | 210.13 | 0 | 0 | 0.004759%
WT-15561 | SE Foundations | Improvement | 2025-09-25 | 2025-09-26 | 1.15 | 0.07 | 1.08 | 0 | 0 | 6.087%
WT-15567 | SE Transactions | Task | 2025-09-24 | 2025-11-19 | 56.88 | 11.75 | 1 | 0 | 44.13 | 20.66%
WT-15581 | SE Transactions | Improvement | 2026-05-14 | 2026-05-14 | 0.54 | 0.06 | 0.48 | 0 | 0 | 11.11%
WT-15617 | SE Transactions | Task | 2025-10-06 | 2025-10-30 | 23.32 | 6.09 | 17.23 | 0 | 0 | 26.11%
WT-15634 | SE Foundations | Build Failure | 2025-10-01 | 2025-10-01 | 0.12 | 0 | 0.12 | 0 | 0 | 0%
WT-15651 | SE Foundations | Task | 2025-10-22 | 2025-10-23 | 1.09 | 1.05 | 0.05 | 0 | 0 | 96.33%
WT-15686 | SE Persistence | Task | 2025-12-08 | 2025-12-08 | 0 | 0 | 0 | 0 | 0
WT-15729 | SE Foundations | Task | 2025-10-12 | 2025-10-23 | 11.47 | 11.47 | 0 | 0 | 0 | 100%
WT-15739 | SE Persistence | Bug | 2025-10-16 | 2025-10-22 | 6.78 | 4.93 | 1.84 | 0 | 0 | 72.71%
WT-15757 | SE Foundations | Task | 2025-10-15 | 2025-10-23 | 8.08 | 8.08 | 0 | 0 | 0 | 100%
WT-15764 | SE Persistence | Task | 2025-10-15 | 2025-10-16 | 1.02 | 0.98 | 0.05 | 0 | 0 | 96.08%
WT-15798 | SE Foundations | Task | 2025-10-16 | 2025-10-17 | 0.24 | 0.15 | 0.09 | 0 | 0 | 62.5%
WT-15803 | SE Transactions | Bug | 2025-10-17 | 2025-10-17 | 0.21 | 0 | 0.21 | 0 | 0 | 0%
WT-15830 | SE Transactions | Task | 2025-10-28 | 2025-10-30 | 1.34 | 0.51 | 0.83 | 0 | 0 | 38.06%
WT-15833 | SE Persistence | Task | 2025-10-27 | 2025-10-29 | 2.14 | 2.14 | 0 | 0 | 0 | 100%
WT-15840 | SE Persistence | Improvement | 2026-02-17 | 2026-02-18 | 1 | 1 | 0 | 0 | 0 | 100%
WT-15853 | SE Foundations | Improvement | 2025-11-21 | 2025-11-23 | 2.82 | 0 | 2.82 | 0 | 0 | 0%
WT-15866 | SE Persistence | Task | 2025-10-30 | 2025-11-05 | 5.92 | 5.64 | 0 | 0 | 0.28 | 95.27%
WT-15867 | SE Persistence | Task | 2025-10-28 | 2025-10-30 | 1.77 | 1.77 | 0 | 0 | 0 | 100%
WT-15869 | SE Persistence | Task | 2025-11-01 | 2025-11-25 | 24.15 | 3.75 | 0.08 | 0 | 20.32 | 15.53%
WT-15873 | SE Persistence | Task | 2025-10-28 | 2025-10-30 | 1.77 | 1.77 | 0 | 0 | 0 | 100%
WT-15874 | SE Persistence | Task | 2025-10-31 | 2025-11-03 | 2.9 | 0.02 | 2.88 | 0 | 0 | 0.6897%
WT-15875 | SE Persistence | Task | 2025-10-30 | 2025-11-18 | 18.1 | 18.1 | 0 | 0 | 0 | 100%
WT-15876 | SE Persistence | Task | 2025-11-01 | 2025-11-24 | 23.95 | 4.18 | 4.5 | 0 | 15.26 | 17.45%
WT-15887 | SE Persistence | Build Failure | 2025-10-30 | 2026-07-21 | 263.56 | 6.3 | 0.55 | 4.37 | 252.34 | 2.39%
WT-15912 | SE Transactions | Improvement | 2025-10-30 | 2025-10-30 | 0.1 | 0.03 | 0.07 | 0 | 0 | 30%
WT-15927 | SE Transactions | Improvement | 2025-11-04 | 2025-11-18 | 14.07 | 3.01 | 11.06 | 0 | 0 | 21.39%
WT-15952 | SE Persistence | Task | 2025-11-11 | 2025-11-13 | 1.91 | 1.75 | 0.16 | 0 | 0 | 91.62%
WT-15997 | SE Persistence | Task | 2025-11-13 | 2025-11-17 | 3.89 | 3.89 | 0 | 0 | 0 | 100%
WT-15998 | SE Persistence | Task | 2025-11-13 | 2025-11-18 | 4.15 | 3.97 | 0 | 0 | 0.18 | 95.66%
WT-16006 | SE Persistence | Task | 2025-11-12 | 2025-11-13 | 0.83 | 0.67 | 0.16 | 0 | 0 | 80.72%
WT-16008 | SE Persistence | Task | 2025-11-12 | 2025-11-13 | 0.79 | 0.63 | 0.16 | 0 | 0 | 79.75%
WT-16017 | SE Transactions | Task | 2025-11-13 | 2025-11-14 | 1.02 | 0.01 | 1.01 | 0 | 0 | 0.9804%
WT-16023 | SE Persistence | Task | 2025-11-14 | 2025-11-17 | 3.01 | 3.01 | 0 | 0 | 0 | 100%
WT-16024 | SE Persistence | Task | 2025-11-14 | 2025-11-18 | 3.87 | 3.87 | 0 | 0 | 0 | 100%
WT-16043 | SE Persistence | Task | 2025-11-18 | 2025-11-19 | 1.83 | 1.83 | 0 | 0 | 0 | 100%
WT-16060 | SE Persistence | Task | 2025-11-20 | 2025-11-20 | 0.9 | 0.37 | 0.53 | 0 | 0 | 41.11%
WT-16061 | SE Transactions | Bug | 2025-12-03 | 2025-12-10 | 6.97 | 6.53 | 0 | 0 | 0.44 | 93.69%
WT-16081 | SE Foundations | Improvement | 2025-11-25 | 2025-11-26 | 1.91 | 0.13 | 1.09 | 0 | 0.69 | 6.806%
WT-16103 | SE Persistence | Improvement | 2025-11-25 | 2025-11-25 | 0.11 | 0.11 | 0 | 0 | 0 | 100%
WT-16105 | SE Persistence | Improvement | 2025-11-25 | 2025-11-25 | 0.64 | 0.64 | 0 | 0 | 0 | 100%
WT-16108 | SE Persistence | Improvement | 2025-11-26 | 2025-11-27 | 0.81 | 0.08 | 0.73 | 0 | 0 | 9.877%
WT-16109 | SE Transactions | Bug | 2025-12-04 | 2025-12-04 | 0 | 0 | 0 | 0 | 0
WT-16115 | SE Persistence | Task | 2025-11-27 | 2025-12-01 | 4.1 | 0.36 | 3.75 | 0 | 0 | 8.78%
WT-16119 | SE Persistence | Improvement | 2025-12-01 | 2025-12-02 | 0.98 | 0.03 | 0.95 | 0 | 0 | 3.061%
WT-16120 | SE Persistence | Improvement | 2025-12-01 | 2025-12-05 | 3.85 | 1.86 | 1.98 | 0 | 0 | 48.31%
WT-16121 | SE Persistence | Improvement | 2025-12-01 | 2025-12-01 | 0.64 | 0.12 | 0.52 | 0 | 0 | 18.75%
WT-16143 | SE Persistence | Improvement | 2025-12-01 | 2025-12-04 | 2.93 | 0.01 | 2.92 | 0 | 0 | 0.3413%
WT-16224 | SE Transactions | Task | 2026-05-19 | 2026-05-26 | 7.9 | 0.08 | 7.81 | 0 | 0 | 1.013%
WT-16230 | SE Transactions | Task | 2025-12-11 | 2025-12-12 | 1.27 | 1.27 | 0 | 0 | 0 | 100%
WT-16231 | SE Transactions | Task | 2026-01-06 | 2026-01-07 | 0.91 | 0.91 | 0 | 0 | 0 | 100%
WT-16239 | SE Transactions | Improvement | 2026-06-01 | 2026-06-05 | 3.28 | 3.28 | 0 | 0 | 0 | 100%
WT-16243 | SE Transactions | Task | 2025-12-11 | 2025-12-12 | 0.9 | 0.04 | 0.86 | 0 | 0 | 4.444%
WT-16320 | SE Persistence | Epic | 2025-12-19 | 2026-01-13 | 25.09 | 25.09 | 0 | 0 | 0 | 100%
WT-16321 | SE Persistence | Bug | 2026-01-08 | 2026-01-12 | 4.02 | 3.29 | 0.73 | 0 | 0 | 81.84%
WT-16323 | SE Persistence | Bug | 2026-01-06 | 2026-01-09 | 3.03 | 1.97 | 1.05 | 0 | 0 | 65.02%
WT-16325 | SE Persistence | Bug | 2026-01-09 | 2026-01-12 | 3.24 | 0.17 | 3.07 | 0 | 0 | 5.247%
WT-16363 | SE Persistence | Task | 2026-01-23 | 2026-01-28 | 4.96 | 4.01 | 0.96 | 0 | 0 | 80.85%
WT-16379 | SE Persistence | Bug | 2025-12-29 | 2026-01-07 | 9.89 | 8.03 | 1.86 | 0 | 0 | 81.19%
WT-16408 | SE Transactions | Improvement | 2026-01-07 | 2026-01-07 | 0.68 | 0 | 0.68 | 0 | 0 | 0%
WT-16410 | SE Transactions | Improvement | 2026-01-07 | 2026-01-13 | 5.62 | 0 | 5.62 | 0 | 0 | 0%
WT-16453 | SE Transactions | Task | 2026-01-13 | 2026-01-14 | 1.15 | 0.01 | 1.14 | 0 | 0 | 0.8696%
WT-16456 | SE Transactions | Task | 2026-01-23 | 2026-01-23 | 0.13 | 0.01 | 0.12 | 0 | 0 | 7.692%
WT-16459 | SE Transactions | Improvement | 2026-04-06 | 2026-04-14 | 7.27 | 0.04 | 7.23 | 0 | 0 | 0.5502%
WT-16498 | SE Transactions | Task | 2026-05-20 | 2026-05-20 | 0.07 | 0.07 | 0 | 0 | 0 | 100%
WT-16516 | SE Transactions | Task | 2026-01-27 | 2026-01-27 | 0.3 | 0.3 | 0 | 0 | 0 | 100%
WT-16522 | SE Persistence | Improvement | 2026-02-23 | 2026-02-26 | 2.9 | 2.89 | 0.01 | 0 | 0 | 99.66%
WT-16581 | SE Transactions | Build Failure | 2026-09-15 | 2026-09-23 | 7.77 | 6.43 | 0 | 0 | 1.35 | 82.75%
WT-16588 | SE Transactions | Task | 2026-02-02 | 2026-02-05 | 3.07 | 1.04 | 2.03 | 0 | 0 | 33.88%
WT-16617 | SE Persistence | Task | 2026-05-08 | 2026-05-08 | 0.01 | 0.01 | 0 | 0 | 0 | 100%
WT-16702 | SE Transactions | Build Failure | 2026-09-02 | 2026-09-02 | 0 | 0 | 0 | 0 | 0
WT-16706 | SE Transactions | Bug | 2026-02-18 | 2026-02-19 | 1.08 | 0 | 1.08 | 0 | 0 | 0%
WT-16716 | SE Transactions | Task | 2026-04-01 | 2026-04-16 | 15.07 | 1.02 | 14.05 | 0 | 0 | 6.768%
WT-16718 | SE Transactions | Task | 2026-06-04 | 2026-06-04 | 0 | 0 | 0 | 0 | 0
WT-16724 | SE Transactions | Task | 2026-02-19 | 2026-02-19 | 0.02 | 0 | 0.02 | 0 | 0 | 0%
WT-16731 | SE Persistence | Bug | 2026-02-20 | 2026-02-22 | 2.89 | 0.01 | 2.88 | 0 | 0 | 0.346%
WT-16742 | SE Transactions | Task | 2026-03-09 | 2026-03-16 | 6.39 | 6.39 | 0 | 0 | 0 | 100%
WT-16764 | SE Transactions | Task | 2026-02-24 | 2026-03-02 | 6.64 | 6.55 | 0 | 0 | 0.08 | 98.64%
WT-16788 | SE Persistence | Sub-task | 2026-03-23 | 2026-06-01 | 70.29 | 15.75 | 0 | 1.93 | 52.6 | 22.41%
WT-16789 | SE Foundations | Task | 2026-04-14 | 2026-05-04 | 20.38 | 6.62 | 13.54 | 0 | 0.22 | 32.48%
WT-16802 | SE Persistence | Task | 2026-03-02 | 2026-03-02 | 0.77 | 0 | 0.77 | 0 | 0 | 0%
WT-16812 | SE Foundations | Task | 2026-05-05 | 2026-05-25 | 19.95 | 1.91 | 18.04 | 0 | 0 | 9.574%
WT-16813 | SE Foundations | Task | 2026-04-30 | 2026-05-21 | 21.06 | 16.56 | 2.93 | 0 | 1.57 | 78.63%
WT-16814 | SE Foundations | Task | 2026-04-24 | 2026-05-19 | 25.13 | 6.76 | 17.98 | 0 | 0.39 | 26.9%
WT-16818 | SE Persistence | Epic | 2026-03-17 | 2026-04-28 | 41.91 | 15.6 | 0 | 0 | 26.31 | 37.22%
WT-16820 | SE Persistence | Task | 2026-03-03 | 2026-03-04 | 0.88 | 0.88 | 0 | 0 | 0 | 100%
WT-16838 | SE Transactions | Task | 2026-09-03 | 2026-09-08 | 4.33 | 0.11 | 4.22 | 0 | 0 | 2.54%
WT-16842 | SE Transactions | Task | 2026-04-15 | 2026-04-21 | 5.9 | 5.64 | 0.25 | 0 | 0 | 95.59%
WT-16850 | SE Transactions | Bug | 2026-03-05 | 2026-03-10 | 4.88 | 0 | 4.88 | 0 | 0 | 0%
WT-16906 | SE Persistence | Task | 2026-03-12 | 2026-03-13 | 0.21 | 0.03 | 0.19 | 0 | 0 | 14.29%
WT-16914 | SE Persistence | Bug | 2026-03-20 | 2026-03-20 | 0.58 | 0.06 | 0.52 | 0 | 0 | 10.34%
WT-16942 | SE Persistence | Task | 2026-03-20 | 2026-03-23 | 3.05 | 3.05 | 0 | 0 | 0 | 100%
WT-16943 | SE Persistence | Task | 2026-03-20 | 2026-03-24 | 4.01 | 4.01 | 0 | 0 | 0 | 100%
WT-16944 | SE Persistence | Task | 2026-03-20 | 2026-03-24 | 3.9 | 3.9 | 0 | 0 | 0 | 100%
WT-16945 | SE Persistence | Task | 2026-03-24 | 2026-03-25 | 1.06 | 1.01 | 0.04 | 0 | 0 | 95.28%
WT-16946 | SE Persistence | Task | 2026-03-25 | 2026-03-30 | 4.89 | 4.89 | 0 | 0 | 0 | 100%
WT-16947 | SE Persistence | Task | 2026-03-31 | 2026-04-13 | 12.8 | 0.97 | 11.83 | 0 | 0 | 7.578%
WT-16948 | SE Persistence | Task | 2026-03-30 | 2026-03-31 | 1.13 | 1.03 | 0.11 | 0 | 0 | 91.15%
WT-16949 | SE Persistence | Task | 2026-04-13 | 2026-04-14 | 1.03 | 1.03 | 0 | 0 | 0 | 100%
WT-16950 | SE Persistence | Task | 2026-04-01 | 2026-04-13 | 11.89 | 0.06 | 11.83 | 0 | 0 | 0.5046%
WT-16951 | SE Persistence | Task | 2026-04-01 | 2026-04-13 | 11.83 | 11.83 | 0 | 0 | 0 | 100%
WT-17001 | SE Persistence | Task | 2026-03-24 | 2026-03-25 | 1.08 | 1.01 | 0.07 | 0 | 0 | 93.52%
WT-17033 | SE Transactions | Technical Debt | 2026-03-31 | 2026-04-07 | 6.28 | 0.04 | 6.24 | 0 | 0 | 0.6369%
WT-17052 | SE Transactions | Task | 2026-03-30 | 2026-05-22 | 53.51 | 1.04 | 52.48 | 0 | 0 | 1.944%
WT-17055 | SE Transactions | New Feature | 2026-04-15 | 2026-04-21 | 6 | 2.24 | 3.76 | 0 | 0 | 37.33%
WT-17057 | SE Transactions | Task | 2026-04-14 | 2026-05-04 | 19.87 | 16.01 | 3.86 | 0 | 0 | 80.57%
WT-17058 | SE Transactions | Task | 2026-04-30 | 2026-06-09 | 40.02 | 27.9 | 12.12 | 0 | 0 | 69.72%
WT-17060 | SE Transactions | Task | 2026-05-04 | 2026-06-16 | 43.05 | 7.72 | 26.86 | 0 | 8.47 | 17.93%
WT-17064 | SE Transactions | Task | 2026-04-28 | 2026-05-07 | 9.82 | 6.58 | 0.97 | 0 | 2.27 | 67.01%
WT-17065 | SE Transactions | Task | 2026-06-02 | 2026-06-04 | 2.08 | 2.08 | 0 | 0 | 0 | 100%
WT-17068 | SE Transactions | Task | 2026-04-02 | 2026-04-21 | 19.32 | 19.32 | 0 | 0 | 0 | 100%
WT-17092 | SE Transactions | Improvement | 2026-04-06 | 2026-04-14 | 7.27 | 0.04 | 7.24 | 0 | 0 | 0.5502%
WT-17133 | SE Foundations | Task | 2026-04-20 | 2026-05-04 | 13.27 | 12.55 | 0.34 | 0 | 0.38 | 94.57%
WT-17158 | SE Transactions | Epic | 2026-05-05 | 2026-06-23 | 49.13 | 21.3 | 0 | 0 | 27.84 | 43.35%
WT-17168 | SE Transactions | Task | 2026-06-04 | 2026-06-04 | 0 | 0 | 0 | 0 | 0
WT-17181 | SE Foundations | Task | 2026-05-28 | 2026-06-05 | 8.05 | 7.14 | 0.91 | 0 | 0 | 88.7%
WT-17182 | SE Transactions | Build Failure | 2026-06-25 | 2026-06-29 | 4.07 | 0.05 | 4.02 | 0 | 0 | 1.229%
WT-17250 | SE Transactions | Task | 2026-06-14 | 2026-06-17 | 3.37 | 0.99 | 2.38 | 0 | 0 | 29.38%
WT-17251 | SE Foundations | Task | 2026-07-03 | 2026-07-07 | 4.14 | 3.03 | 1.11 | 0 | 0 | 73.19%
WT-17263 | SE Foundations | Task | 2026-07-02 | 2026-07-06 | 4.2 | 0.01 | 4.2 | 0 | 0 | 0.2381%
WT-17269 | SE Persistence | Bug | 2026-04-22 | 2026-04-24 | 1.28 | 1.24 | 0.04 | 0 | 0 | 96.88%
WT-17272 | SE Foundations | Bug | 2026-05-04 | 2026-05-22 | 17.86 | 3.84 | 14.02 | 0 | 0 | 21.5%
WT-17274 | SE Transactions | Task | 2026-05-19 | 2026-05-29 | 10.25 | 10.25 | 0 | 0 | 0 | 100%
WT-17276 | SE Transactions | Task | 2026-06-02 | 2026-06-05 | 2.92 | 2.92 | 0 | 0 | 0 | 100%
WT-17296 | SE Transactions | Task | 2026-05-07 | 2026-05-27 | 19.12 | 4.76 | 8.93 | 0 | 5.43 | 24.9%
WT-17297 | SE Transactions | Bug | 2026-04-23 | 2026-04-24 | 0.72 | 0.1 | 0.62 | 0 | 0 | 13.89%
WT-17347 | SE Foundations | Task | 2026-05-03 | 2026-05-06 | 2.46 | 0.07 | 2.39 | 0 | 0 | 2.846%
WT-17362 | SE Persistence | Bug | 2026-05-01 | 2026-05-04 | 2.91 | 0.02 | 2.89 | 0 | 0 | 0.6873%
WT-17366 | SE Transactions | Build Failure | 2026-08-11 | 2026-08-11 | 0.92 | 0 | 0.92 | 0 | 0 | 0%
WT-17394 | SE Foundations | Task | 2026-05-05 | 2026-05-07 | 2.96 | 2.96 | 0 | 0 | 0 | 100%
WT-17397 | SE Transactions | Bug | 2026-05-05 | 2026-05-05 | 0.01 | 0.01 | 0 | 0 | 0 | 100%
WT-17404 | SE Transactions | Bug | 2026-05-05 | 2026-05-06 | 0.14 | 0 | 0.14 | 0 | 0 | 0%
WT-17412 | SE Transactions | Bug | 2026-07-22 | 2026-07-23 | 1.01 | 0.08 | 0.94 | 0 | 0 | 7.921%
WT-17417 | SE Transactions | Bug | 2026-05-18 | 2026-05-19 | 0.88 | 0 | 0.87 | 0 | 0 | 0%
WT-17422 | SE Transactions | Task | 2026-06-15 | 2026-06-19 | 3.36 | 3.26 | 0.1 | 0 | 0 | 97.02%
WT-17426 | SE Transactions | Build Failure | 2026-05-25 | 2026-08-20 | 87.28 | 17.58 | 17.13 | 0 | 52.57 | 20.14%
WT-17437 | SE Transactions | Task | 2026-06-15 | 2026-06-18 | 2.25 | 2.25 | 0 | 0 | 0 | 100%
WT-17439 | SE Foundations | Task | 2026-06-01 | 2026-06-08 | 7.61 | 7.61 | 0 | 0 | 0 | 100%
WT-17440 | SE Foundations | Task | 2026-05-25 | 2026-06-08 | 14.91 | 14.91 | 0 | 0 | 0 | 100%
WT-17459 | SE Transactions | Build Failure | 2026-05-18 | 2026-05-20 | 1.91 | 0 | 1.91 | 0 | 0 | 0%
WT-17471 | SE Transactions | Build Failure | 2026-07-13 | 2026-07-13 | 0.69 | 0.01 | 0.68 | 0 | 0 | 1.449%
WT-17477 | SE Foundations | Task | 2026-05-12 | 2026-05-25 | 12.97 | 12.97 | 0 | 0 | 0 | 100%
WT-17485 | SE Transactions | Task | 2026-05-19 | 2026-05-20 | 0.87 | 0.82 | 0.05 | 0 | 0 | 94.25%
WT-17504 | SE Foundations | Sub-task | 2026-05-13 | 2026-05-22 | 9.02 | 6.43 | 0.2 | 0 | 2.39 | 71.29%
WT-17515 | SE Transactions | Task | 2026-05-14 | 2026-05-19 | 5.04 | 0.02 | 5.02 | 0 | 0 | 0.3968%
WT-17528 | SE Foundations | Task | 2026-05-14 | 2026-05-26 | 12.09 | 6.63 | 0.43 | 0 | 4.27 | 54.84%
WT-17535 | SE Foundations | Task | 2026-05-21 | 2026-06-02 | 11.56 | 7.74 | 3.82 | 0 | 0 | 66.96%
WT-17536 | SE Foundations | Task | 2026-06-02 | 2026-06-05 | 3.01 | 0.27 | 2.74 | 0 | 0 | 8.97%
WT-17537 | SE Foundations | Task | 2026-05-26 | 2026-06-01 | 5.14 | 0.26 | 4.89 | 0 | 0 | 5.058%
WT-17538 | SE Foundations | Task | 2026-06-05 | 2026-06-16 | 11.22 | 6.1 | 5.12 | 0 | 0 | 54.37%
WT-17539 | SE Foundations | Task | 2026-06-11 | 2026-06-21 | 10 | 4.34 | 5.66 | 0 | 0 | 43.4%
WT-17540 | SE Foundations | Task | 2026-06-01 | 2026-06-02 | 1.68 | 0.86 | 0.82 | 0 | 0 | 51.19%
WT-17544 | SE Transactions | Bug | 2026-05-15 | 2026-05-15 | 0.1 | 0 | 0.1 | 0 | 0 | 0%
WT-17567 | SE Transactions | Bug | 2026-05-22 | 2026-06-09 | 18.1 | 12.13 | 4.13 | 0 | 1.85 | 67.02%
WT-17572 | SE Transactions | Task | 2026-05-19 | 2026-05-19 | 0.25 | 0 | 0.25 | 0 | 0 | 0%
WT-17574 | SE Transactions | Build Failure | 2026-07-10 | 2026-07-15 | 5.14 | 2.98 | 0.2 | 0 | 1.96 | 57.98%
WT-17576 | SE Transactions | Build Failure | 2026-05-20 | 2026-05-21 | 1.1 | 0.89 | 0.21 | 0 | 0 | 80.91%
WT-17577 | SE Transactions | Build Failure | 2026-06-10 | 2026-06-16 | 6.39 | 0.01 | 6.38 | 0 | 0 | 0.1565%
WT-17582 | SE Transactions | Task | 2026-05-19 | 2026-05-20 | 0.45 | 0.06 | 0.39 | 0 | 0 | 13.33%
WT-17586 | SE Transactions | Bug | 2026-05-20 | 2026-05-21 | 0.96 | 0.02 | 0.94 | 0 | 0 | 2.083%
WT-17590 | SE Transactions | Improvement | 2026-05-20 | 2026-05-26 | 5.72 | 0.59 | 5.13 | 0 | 0 | 10.31%
WT-17591 | SE Transactions | Task | 2026-05-20 | 2026-05-22 | 1.62 | 0.03 | 1.59 | 0 | 0 | 1.852%
WT-17601 | SE Transactions | Task | 2026-05-22 | 2026-05-29 | 6.83 | 0.11 | 6.73 | 0 | 0 | 1.611%
WT-17607 | SE Transactions | Build Failure | 2026-05-26 | 2026-05-26 | 0.08 | 0.08 | 0 | 0 | 0 | 100%
WT-17617 | SE Foundations | Task | 2026-06-11 | 2026-07-22 | 41.34 | 41.34 | 0 | 0 | 0 | 100%
WT-17651 | SE Transactions | Task | 2026-05-26 | 2026-05-26 | 0.39 | 0 | 0.39 | 0 | 0 | 0%
WT-17655 | SE Transactions | Build Failure | 2026-09-01 | 2026-10-07 | 36.94 | 1.05 | 0 | 35.34 | 0.54 | 2.842%
WT-17677 | SE Transactions | Task | 2026-07-23 | 2026-08-14 | 22.09 | 21.45 | 0.64 | 0 | 0 | 97.1%
WT-17680 | SE Transactions | Improvement | 2026-06-23 | 2026-07-04 | 11.06 | 11.06 | 0 | 0 | 0 | 100%
WT-17681 | SE Transactions | Improvement | 2026-07-07 | 2026-08-13 | 37.23 | 14.9 | 0 | 0 | 22.34 | 40.02%
WT-17689 | SE Transactions | Task | 2026-06-04 | 2026-06-09 | 4.86 | 0.74 | 4.12 | 0 | 0 | 15.23%
WT-17706 | SE Transactions | Bug | 2026-06-01 | 2026-06-02 | 1.04 | 0 | 1.04 | 0 | 0 | 0%
WT-17712 | SE Foundations | Task | 2026-06-01 | 2026-06-01 | 0.02 | 0.02 | 0 | 0 | 0 | 100%
WT-17737 | SE Transactions | Improvement | 2026-07-29 | 2026-08-25 | 27.14 | 27.14 | 0 | 0 | 0 | 100%
WT-17753 | SE Foundations | Technical Debt | 2026-06-05 | 2026-06-10 | 4.91 | 3.86 | 1.04 | 0 | 0 | 78.62%
WT-17755 | SE Foundations | Task | 2026-06-09 | 2026-06-29 | 20.2 | 17.18 | 3.01 | 0 | 0 | 85.05%
WT-17757 | SE Transactions | Task | 2026-07-23 | 2026-08-10 | 18.15 | 18.15 | 0 | 0 | 0 | 100%
WT-17773 | SE Foundations | Task | 2026-10-14 | 2026-10-14 | 0.05 | 0.05 | 0 | 0 | 0 | 100%
WT-17780 | SE Transactions | Task | 2026-06-09 | 2026-06-12 | 3.08 | 0.06 | 3.02 | 0 | 0 | 1.948%
WT-17782 | SE Foundations | Task | 2026-06-15 | 2026-06-19 | 3.74 | 0.03 | 3.71 | 0 | 0 | 0.8021%
WT-17784 | SE Foundations | Task | 2026-06-16 | 2026-06-25 | 8.94 | 0.89 | 8.05 | 0 | 0 | 9.955%
WT-17785 | SE Foundations | Task | 2026-06-09 | 2026-07-14 | 35.09 | 34.85 | 0.24 | 0 | 0 | 99.32%
WT-17786 | SE Foundations | Task | 2026-06-09 | 2026-06-22 | 13.61 | 13.61 | 0 | 0 | 0 | 100%
WT-17788 | SE Transactions | Improvement | 2026-09-03 | 2026-09-03 | 0.28 | 0.03 | 0.26 | 0 | 0 | 10.71%
WT-17790 | SE Foundations | Task | 2026-07-30 | 2026-08-04 | 5.68 | 5.68 | 0 | 0 | 0 | 100%
WT-17799 | SE Transactions | Build Failure | 2026-07-23 | 2026-07-29 | 5.81 | 5.81 | 0 | 0 | 0 | 100%
WT-17813 | SE Transactions | Task | 2026-06-12 | 2026-06-19 | 6.72 | 5.68 | 1.04 | 0 | 0 | 84.52%
WT-17817 | SE Foundations | Bug | 2026-07-01 | 2026-07-08 | 7.77 | 4.91 | 0.58 | 0 | 0.66 | 63.19%
WT-17820 | SE Transactions | Bug | 2026-07-01 | 2026-07-13 | 12.32 | 8.27 | 0 | 0 | 0.37 | 67.13%
WT-17858 | SE Foundations | Task | 2026-06-22 | 2026-06-26 | 4.01 | 0.02 | 3.99 | 0 | 0 | 0.4988%
WT-17859 | SE Transactions | Task | 2026-06-17 | 2026-06-19 | 1.7 | 0 | 1.69 | 0 | 0 | 0%
WT-17862 | SE Transactions | Task | 2026-06-18 | 2026-06-18 | 0.25 | 0.08 | 0.16 | 0 | 0 | 32%
WT-17870 | SE Foundations | Build Failure | 2026-07-01 | 2026-07-03 | 2.04 | 2.03 | 0.02 | 0 | 0 | 99.51%
WT-17875 | SE Foundations | Build Failure | 2026-07-08 | 2026-07-09 | 1.11 | 1.11 | 0 | 0 | 0 | 100%
WT-17878 | SE Transactions | Build Failure | 2026-07-06 | 2026-07-20 | 14.24 | 10.27 | 0.05 | 0 | 3.92 | 72.12%
WT-17880 | SE Foundations | Bug | 2026-07-30 | 2026-08-03 | 3.72 | 0.92 | 2.8 | 0 | 0 | 24.73%
WT-17881 | SE Foundations | Task | 2026-06-22 | 2026-06-30 | 7.97 | 7.97 | 0 | 0 | 0 | 100%
WT-17895 | SE Foundations | Task | 2026-06-29 | 2026-07-29 | 30.8 | 18.21 | 12.6 | 0 | 0 | 59.12%
WT-17896 | SE Foundations | Task | 2026-07-02 | 2026-07-14 | 11.78 | 0 | 11.78 | 0 | 0 | 0%
WT-17897 | SE Foundations | Task | 2026-07-05 | 2026-07-30 | 24.42 | 7.41 | 17.01 | 0 | 0 | 30.34%
WT-17919 | SE Transactions | Task | 2026-06-29 | 2026-06-30 | 0.95 | 0.04 | 0.92 | 0 | 0 | 4.211%
WT-17933 | SE Foundations | Bug | 2026-07-01 | 2026-08-06 | 35.65 | 13.15 | 7.04 | 15.32 | 0.13 | 36.89%
WT-17939 | SE Transactions | Task | 2026-06-30 | 2026-07-01 | 1.18 | 0.24 | 0.95 | 0 | 0 | 20.34%
WT-17942 | SE Transactions | Task | 2026-09-14 | 2026-09-14 | 0 | 0 | 0 | 0 | 0
WT-17955 | SE Foundations | Task | 2026-08-07 | 2026-08-13 | 6.01 | 5.06 | 0.95 | 0 | 0 | 84.19%
WT-17959 | SE Foundations | Task | 2026-07-02 | 2026-07-06 | 4.3 | 0.01 | 4.3 | 0 | 0 | 0.2326%
WT-17962 | SE Foundations | Build Failure | 2026-07-07 | 2026-07-16 | 9.71 | 3.86 | 2.68 | 0 | 3.17 | 39.75%
WT-17964 | SE Transactions | Task | 2026-09-10 | 2026-09-11 | 0.07 | 0.07 | 0 | 0 | 0 | 100%
WT-17974 | SE Foundations | Task | 2026-07-27 | 2026-07-30 | 2.77 | 2.77 | 0 | 0 | 0 | 100%
WT-17975 | SE Foundations | Task | 2026-07-27 | 2026-07-28 | 0.86 | 0.86 | 0 | 0 | 0 | 100%
WT-17976 | SE Foundations | Task | 2026-07-27 | 2026-07-28 | 0.86 | 0.86 | 0 | 0 | 0 | 100%
WT-17979 | SE Transactions | Build Failure | 2026-09-01 | 2026-09-10 | 9.23 | 2.92 | 0 | 0 | 6.3 | 31.64%
WT-17982 | SE Transactions | Task | 2026-07-24 | 2026-08-14 | 21.01 | 21.01 | 0 | 0 | 0 | 100%
WT-17984 | SE Foundations | Build Failure | 2026-07-09 | 2026-07-13 | 3.89 | 0.9 | 3 | 0 | 0 | 23.14%
WT-17985 | SE Transactions | Task | 2026-07-05 | 2026-07-07 | 1.79 | 0 | 1.79 | 0 | 0 | 0%
WT-17989 | SE Transactions | Bug | 2026-07-06 | 2026-07-14 | 8.09 | 8.05 | 0.05 | 0 | 0 | 99.51%
WT-17998 | SE Foundations | Build Failure | 2026-07-15 | 2026-07-20 | 5.74 | 5.53 | 0 | 0 | 0.21 | 96.34%
WT-18006 | SE Transactions | Improvement | 2026-08-26 | 2026-09-01 | 6.15 | 6.15 | 0 | 0 | 0 | 100%
WT-18014 | SE Transactions | Task | 2026-07-08 | 2026-07-10 | 1.81 | 0.07 | 1.74 | 0 | 0 | 3.867%
WT-18021 | SE Transactions | Task | 2026-07-13 | 2026-07-15 | 1.89 | 0 | 1.89 | 0 | 0 | 0%
WT-18029 | SE Foundations | Task | 2026-07-15 | 2026-07-22 | 7.24 | 0 | 7.24 | 0 | 0 | 0%
WT-18031 | SE Foundations | Task | 2026-09-17 | 2026-09-24 | 7.93 | 3.97 | 3.96 | 0 | 0 | 50.06%
WT-18044 | SE Transactions | Task | 2026-07-15 | 2026-08-20 | 35.4 | 5.48 | 13.16 | 16.76 | 0 | 15.48%
WT-18045 | SE Transactions | Task | 2026-08-24 | 2026-08-28 | 3.11 | 1 | 2.11 | 0 | 0 | 32.15%
WT-18049 | SE Transactions | Build Failure | 2026-08-17 | 2026-08-17 | 0.78 | 0 | 0.78 | 0 | 0 | 0%
WT-18065 | SE Foundations | Task | 2026-07-13 | 2026-07-27 | 13.15 | 13.15 | 0 | 0 | 0 | 100%
WT-18066 | SE Foundations | Task | 2026-07-13 | 2026-07-21 | 7.04 | 7.04 | 0 | 0 | 0 | 100%
WT-18068 | SE Foundations | Bug | 2026-08-17 | 2026-09-22 | 35.51 | 2.9 | 15.69 | 0 | 16.92 | 8.167%
WT-18069 | SE Transactions | Build Failure | 2026-07-17 | 2026-07-17 | 0.39 | 0.25 | 0.15 | 0 | 0 | 64.1%
WT-18080 | SE Transactions | Task | 2026-09-14 | 2026-09-19 | 4.95 | 4.91 | 0.04 | 0 | 0 | 99.19%
WT-18114 | SE Transactions | Build Failure | 2026-08-05 | 2026-08-21 | 16.02 | 0.02 | 6.38 | 0 | 0.02 | 0.1248%
WT-18118 | SE Foundations | Task | 2026-09-28 | 2026-09-28 | 0.19 | 0.1 | 0.1 | 0 | 0 | 52.63%
WT-18125 | SE Transactions | Build Failure | 2026-07-19 | 2026-07-23 | 3.1 | 2.07 | 1.03 | 0 | 0 | 66.77%
WT-18150 | SE Foundations | Task | 2026-07-29 | 2026-08-06 | 8.28 | 6 | 1.15 | 0 | 1.13 | 72.46%
WT-18155 | SE Foundations | Task | 2026-07-22 | 2026-08-06 | 15.19 | 5.88 | 9.31 | 0 | 0 | 38.71%
WT-18156 | SE Transactions | Bug | 2026-07-26 | 2026-08-07 | 11.27 | 8.08 | 3.18 | 0 | 0 | 71.69%
WT-18158 | SE Transactions | Improvement | 2026-08-18 | 2026-08-19 | 1.18 | 1.18 | 0 | 0 | 0 | 100%
WT-18162 | SE Transactions | Improvement | 2026-07-23 | 2026-07-24 | 1.34 | 0 | 0.18 | 0 | 0.18 | 0%
WT-18168 | SE Transactions | Bug | 2026-08-06 | 2026-08-10 | 3.86 | 3.77 | 0.09 | 0 | 0 | 97.67%
WT-18169 | SE Transactions | Task | 2026-07-23 | 2026-07-27 | 3.56 | 0.44 | 3.12 | 0 | 0 | 12.36%
WT-18172 | SE Transactions | Bug | 2026-09-10 | 2026-09-10 | 0.17 | 0.06 | 0.1 | 0 | 0 | 35.29%
WT-18173 | SE Foundations | Bug | 2026-07-24 | 2026-08-03 | 9.86 | 6.82 | 3.03 | 0 | 0 | 69.17%
WT-18179 | SE Foundations | Bug | 2026-07-30 | 2026-08-17 | 17.98 | 11.93 | 6.05 | 0 | 0 | 66.35%
WT-18205 | SE Foundations | Task | 2026-08-05 | 2026-08-06 | 1.01 | 0 | 0.26 | 0 | 0.21 | 0%
WT-18214 | SE Foundations | Task | 2026-07-29 | 2026-07-31 | 1.28 | 0.25 | 0.87 | 0 | 0.1 | 19.53%
WT-18220 | SE Transactions | Task | 2026-07-30 | 2026-07-30 | 0.07 | 0.07 | 0 | 0 | 0 | 100%
WT-18223 | SE Transactions | Build Failure | 2026-08-21 | 2026-08-21 | 0.17 | 0.01 | 0.16 | 0 | 0 | 5.882%
WT-18225 | SE Foundations | Task | 2026-07-31 | 2026-08-03 | 3.56 | 2.33 | 1.22 | 0 | 0 | 65.45%
WT-18230 | SE Foundations | Build Failure | 2026-07-31 | 2026-08-13 | 13.18 | 5.19 | 7.99 | 0 | 0 | 39.38%
WT-18238 | SE Transactions | Build Failure | 2026-08-03 | 2026-08-04 | 0.93 | 0.93 | 0 | 0 | 0 | 100%
WT-18241 | SE Transactions | Build Failure | 2026-08-18 | 2026-08-25 | 6.88 | 6.88 | 0 | 0 | 0 | 100%
WT-18242 | SE Transactions | Task | 2026-08-03 | 2026-08-03 | 0.14 | 0.01 | 0.13 | 0 | 0 | 7.143%
WT-18250 | SE Transactions | Build Failure | 2026-09-11 | 2026-09-11 | 0.07 | 0.07 | 0 | 0 | 0 | 100%
WT-18252 | SE Foundations | Task | 2026-08-04 | 2026-08-05 | 0.04 | 0.04 | 0 | 0 | 0 | 100%
WT-18253 | SE Transactions | Bug | 2026-08-11 | 2026-08-18 | 6.86 | 6.74 | 0.13 | 0 | 0 | 98.25%
WT-18255 | SE Transactions | Build Failure | 2026-08-26 | 2026-10-01 | 36.52 | 6.36 | 0 | 0 | 30.16 | 17.42%
WT-18257 | SE Foundations | Task | 2026-08-07 | 2026-08-11 | 4.09 | 4.09 | 0 | 0 | 0 | 100%
WT-18258 | SE Foundations | Task | 2026-08-05 | 2026-08-14 | 9.5 | 6.29 | 3.21 | 0 | 0 | 66.21%
WT-18259 | SE Foundations | Task | 2026-08-04 | 2026-08-19 | 14.92 | 14.71 | 0 | 0 | 0.21 | 98.59%
WT-18267 | SE Foundations | Task | 2026-09-21 | 2026-09-30 | 8.04 | 3 | 5.05 | 0 | 0 | 37.31%
WT-18270 | SE Foundations | Improvement | 2026-08-05 | 2026-08-05 | 0.13 | 0 | 0.13 | 0 | 0 | 0%
WT-18274 | SE Foundations | Bug | 2026-08-06 | 2026-08-12 | 5.03 | 3.45 | 1.58 | 0 | 0 | 68.59%
WT-18282 | SE Foundations | Sub-task | 2026-08-06 | 2026-08-10 | 3.45 | 0 | 3.44 | 0 | 0 | 0%
WT-18300 | SE Transactions | Build Failure | 2026-08-21 | 2026-09-07 | 16.78 | 0.32 | 10.64 | 0 | 3.16 | 1.907%
WT-18301 | SE Transactions | Build Failure | 2026-08-10 | 2026-08-10 | 0.92 | 0.22 | 0.7 | 0 | 0 | 23.91%
WT-18306 | SE Transactions | Build Failure | 2026-08-18 | 2026-08-20 | 1.39 | 1.29 | 0.11 | 0 | 0 | 92.81%
WT-18308 | SE Transactions | Task | 2026-08-21 | 2026-09-07 | 16.47 | 16.47 | 0 | 0 | 0 | 100%
WT-18320 | SE Foundations | Task | 2026-08-14 | 2026-08-25 | 11.22 | 9.92 | 1.29 | 0 | 0 | 88.41%
WT-18324 | SE Foundations | Bug | 2026-08-12 | 2026-08-28 | 16.43 | 10.51 | 5.92 | 0 | 0 | 63.97%
WT-18331 | SE Transactions | Bug | 2026-08-12 | 2026-08-14 | 1.19 | 0.07 | 0.99 | 0 | 0.13 | 5.882%
WT-18334 | SE Foundations | Bug | 2026-08-26 | 2026-09-07 | 11.97 | 1.22 | 0 | 10.75 | 0 | 10.19%
WT-18339 | SE Foundations | Bug | 2026-08-19 | 2026-08-19 | 0.13 | 0.13 | 0 | 0 | 0 | 100%
WT-18343 | SE Foundations | Task | 2026-09-24 | 2026-09-28 | 3.09 | 3.09 | 0 | 0 | 0 | 100%
WT-18350 | SE Transactions | Bug | 2026-08-18 | 2026-08-18 | 0.12 | 0.01 | 0.1 | 0 | 0 | 8.333%
WT-18351 | SE Transactions | Bug | 2026-08-19 | 2026-08-19 | 0.2 | 0.04 | 0.17 | 0 | 0 | 20%
WT-18369 | SE Foundations | Bug | 2026-08-18 | 2026-08-26 | 7.45 | 2.66 | 4.78 | 0 | 0 | 35.7%
WT-18378 | SE Transactions | Build Failure | 2026-09-01 | 2026-09-10 | 9.09 | 1.88 | 7.22 | 0 | 0 | 20.68%
WT-18384 | SE Foundations | Bug | 2026-08-18 | 2026-08-20 | 1.94 | 1.94 | 0 | 0 | 0 | 100%
WT-18400 | SE Transactions | Improvement | 2026-08-24 | 2026-09-10 | 17.14 | 15.25 | 1.89 | 0 | 0 | 88.97%
WT-18403 | SE Foundations | Task | 2026-09-21 | 2026-09-21 | 0.28 | 0.21 | 0.07 | 0 | 0 | 75%
WT-18405 | SE Foundations | Bug | 2026-08-19 | 2026-09-17 | 28.93 | 12.71 | 9.2 | 0 | 3.07 | 43.93%
WT-18406 | SE Transactions | Task | 2026-08-20 | 2026-08-31 | 11.57 | 11.57 | 0 | 0 | 0 | 100%
WT-18410 | SE Transactions | Bug | 2026-08-19 | 2026-08-25 | 5.82 | 1.9 | 3.92 | 0 | 0 | 32.65%
WT-18415 | SE Foundations | Build Failure | 2026-08-25 | 2026-08-27 | 1.17 | 0.28 | 0.88 | 0 | 0 | 23.93%
WT-18425 | SE Transactions | Improvement | 2026-09-07 | 2026-09-24 | 16.86 | 15.77 | 1.09 | 0 | 0 | 93.53%
WT-18430 | SE Transactions | Task | 2026-09-21 | 2026-09-23 | 1.7 | 0.67 | 1.03 | 0 | 0 | 39.41%
WT-18458 | SE Transactions | Bug | 2026-08-25 | 2026-09-04 | 10.07 | 5.98 | 1.25 | 0 | 0.77 | 59.38%
WT-18466 | SE Transactions | Build Failure | 2026-09-03 | 2026-09-04 | 1.08 | 1.08 | 0 | 0 | 0 | 100%
WT-18468 | SE Transactions | Improvement | 2026-09-18 | 2026-09-22 | 3.97 | 3.79 | 0.18 | 0 | 0 | 95.47%
WT-18495 | SE Transactions | Bug | 2026-08-27 | 2026-08-29 | 1.7 | 1.7 | 0 | 0 | 0 | 100%
WT-18496 | SE Transactions | Bug | 2026-08-27 | 2026-08-29 | 1.81 | 1.81 | 0 | 0 | 0 | 100%
WT-18501 | SE Foundations | Task | 2026-09-29 | 2026-10-09 | 9.96 | 7.62 | 1.95 | 0 | 0.39 | 76.51%
WT-18502 | SE Transactions | Build Failure | 2026-09-01 | 2026-09-02 | 0.7 | 0.7 | 0 | 0 | 0 | 100%
WT-18512 | SE Transactions | Bug | 2026-08-28 | 2026-09-10 | 13.2 | 6.05 | 2.02 | 0 | 5.14 | 45.83%
WT-18515 | SE Foundations | Task | 2026-08-28 | 2026-09-08 | 10.85 | 5.87 | 4.98 | 0 | 0 | 54.1%
WT-18520 | SE Foundations | Bug | 2026-08-30 | 2026-08-31 | 0.77 | 0.04 | 0.73 | 0 | 0 | 5.195%
WT-18521 | SE Foundations | Sub-task | 2026-08-30 | 2026-09-02 | 2.09 | 0.06 | 2.03 | 0 | 0 | 2.871%
WT-18543 | SE Transactions | Improvement | 2026-09-01 | 2026-09-03 | 1.77 | 0.79 | 0.98 | 0 | 0 | 44.63%
WT-18559 | SE Transactions | Improvement | 2026-09-04 | 2026-09-11 | 6.88 | 0.1 | 6.78 | 0 | 0 | 1.453%
WT-18565 | SE Transactions | Task | 2026-09-14 | 2026-10-12 | 27.72 | 27.72 | 0 | 0 | 0 | 100%
WT-18572 | SE Transactions | Bug | 2026-09-07 | 2026-09-08 | 0.99 | 0.04 | 0.94 | 0 | 0 | 4.04%
WT-18579 | SE Transactions | Bug | 2026-09-08 | 2026-09-10 | 2.96 | 0 | 1.3 | 0 | 0.21 | 0%
WT-18603 | SE Transactions | Build Failure | 2026-09-15 | 2026-10-08 | 23.42 | 0 | 23.42 | 0 | 0 | 0%
WT-18609 | SE Transactions | Task | 2026-09-10 | 2026-09-10 | 0.11 | 0.11 | 0 | 0 | 0 | 100%
WT-18615 | SE Transactions | Build Failure | 2026-09-11 | 2026-09-11 | 0.4 | 0.4 | 0 | 0 | 0 | 100%
WT-18638 | SE Foundations | Task | 2026-09-24 | 2026-10-12 | 18.08 | 5.92 | 12.16 | 0 | 0 | 32.74%
WT-18639 | SE Foundations | Task | 2026-09-30 | 2026-10-12 | 12.06 | 6.91 | 5.14 | 0 | 0 | 57.3%
WT-18645 | SE Transactions | Improvement | 2026-09-14 | 2026-09-30 | 15.69 | 0 | 15.69 | 0 | 0 | 0%
WT-18653 | SE Transactions | Task | 2026-09-18 | 2026-09-25 | 6.97 | 6.97 | 0 | 0 | 0 | 100%
WT-18704 | SE Foundations | Bug | 2026-09-28 | 2026-10-01 | 3.01 | 1.87 | 1.14 | 0 | 0 | 62.13%
WT-18705 | SE Foundations | Bug | 2026-09-28 | 2026-10-08 | 10.86 | 7.87 | 3 | 0 | 0 | 72.47%
WT-18724 | SE Transactions | Build Failure | 2026-09-25 | 2026-10-11 | 16.89 | 11.32 | 0 | 0 | 5.56 | 67.02%
WT-18727 | SE Foundations | Task | 2026-09-23 | 2026-09-24 | 0.99 | 0.06 | 0.93 | 0 | 0 | 6.061%
WT-18734 | SE Foundations | Task | 2026-09-24 | 2026-10-01 | 6.74 | 4.64 | 0.36 | 0 | 0.04 | 68.84%
WT-18737 | SE Foundations | Task | 2026-09-24 | 2026-09-25 | 0.75 | 0.57 | 0.18 | 0 | 0 | 76%
WT-18743 | SE Foundations | Bug | 2026-09-25 | 2026-10-01 | 6.77 | 2.95 | 3.83 | 0 | 0 | 43.57%
WT-18773 | SE Transactions | Bug | 2026-09-29 | 2026-10-02 | 3.1 | 1.02 | 1.09 | 0 | 0.06 | 32.9%
WT-18790 | SE Transactions | Task | 2026-10-07 | 2026-10-12 | 5.06 | 5.06 | 0 | 0 | 0 | 100%
WT-18803 | SE Transactions | Task | 2026-10-09 | 2026-10-09 | 0.16 | 0.03 | 0.13 | 0 | 0 | 18.75%
WT-18804 | SE Transactions | Bug | 2026-10-06 | 2026-10-12 | 5.48 | 1.11 | 4.37 | 0 | 0 | 20.26%
|  |  |  | Median | 4.145
|  |  |  | 85th pct | 18.1985
|  |  |  | Review share | 23.24%

## Capacity planner
Sprint capacity planner
From the Sprint Planning Field Guide. Change the blue cells.
People on the team | 6
Working days in the sprint | 10
Leave and holiday days (team total) | 4
Meeting days (team total) | 6
Focus factor | 70%
Commit level | 80%
Unplanned work buffer | 20%
Raw person-days | 60
Available person-days | 50
Real capacity (after focus factor) | 35
Reserved for unplanned work | 7
Commit up to (person-days) | 22.4